## Survey Timeline
TIMELINE (Weeks respective to Survey Go-live)
TASK | ASSIGNED TO | PROGRESS | Start | End | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Pre-survey Planning
Engage with Survey Vendor
Establish Survey Goals (response rates, action item success, etc.)
Establish Survey Criteria (demographics, who to include/exclude, etc.)
Determine Survey Questions
Unit Mapping (HR / IT Data Management)
Data Analytics
Identify Action Planning Triads
Test Survey Link (to ensure accessibility to all intended participants)
Pre-survey Education
Leadership Support for Action Planning
Town Hall Meeting
Staff Meetings
Committee Roadshow
FAQs
Marketing Campaign
Staff Newsletters
Screensavers & Banners
Distribute Flyers & Chocolate
During Survey
Survey Go-live
Marketing
Staff Reminders
Progress Reports
Post Survey
Analyze Survey Findings
Disseminate Survey Results
Action Planning (See Next Tab)

## Action Planning Timeline
TIMELINE (Weeks respective to Survey Go-live)
TASK | ASSIGNED TO | PROGRESS | Start | End | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Pre-survey Prep
Identify & Engage Action Planning Triads | bar: TIMELINE (Weeks respective to Survey Go-live) -4
Establish Executive Leadership Commitment | bar: TIMELINE (Weeks respective to Survey Go-live) -4 to TIMELINE (Weeks respective to Survey Go-live) -3
Executive Leadership Requests Triad Support | bar: TIMELINE (Weeks respective to Survey Go-live) -1
Action Planning Prep
Sendout Action Planning Meeting Availability Poll | bar: TIMELINE (Weeks respective to Survey Go-live) 1
Send Meeting Invite | bar: TIMELINE (Weeks respective to Survey Go-live) 2
Send Email to Action Planning Triads with Results | bar: TIMELINE (Weeks respective to Survey Go-live) 3
Send Meeting Agenda & Reminder Email | bar: TIMELINE (Weeks respective to Survey Go-live) 5
Action Planning Meeting
Introduction
Thank You for Particpating
Review Survey Goals
Survey Results Overview
Top Strengths and Themes
Top Opportunities and Themes
Action Planning
Discussion (contributing factors / root causes)
Brainstorm Action Items
Identify ONE Strong and Feasible Action Item
Establish Action Item Owner and Due Date
Follow-up
Check-in with Action Item Owners (ad-hoc) | bar: TIMELINE (Weeks respective to Survey Go-live) 10; TIMELINE (Weeks respective to Survey Go-live) 14; TIMELINE (Weeks respective to Survey Go-live) 18
Disseminate Action Items & Status with Organization | bar: TIMELINE (Weeks respective to Survey Go-live) 7 to TIMELINE (Weeks respective to Survey Go-live) 8; TIMELINE (Weeks respective to Survey Go-live) 11; TIMELINE (Weeks respective to Survey Go-live) 15; TIMELINE (Weeks respective to Survey Go-live) 19
**Executive Leadership Follow-up | bar: TIMELINE (Weeks respective to Survey Go-live) 6 to TIMELINE (Weeks respective to Survey Go-live) 24
3-month Checkback | bar: TIMELINE (Weeks respective to Survey Go-live) 18 to TIMELINE (Weeks respective to Survey Go-live) 20
Collect Feedback from Traid Groups on Process | bar: TIMELINE (Weeks respective to Survey Go-live) 18 to TIMELINE (Weeks respective to Survey Go-live) 24
**Lesson learned: obtain this committent during the pre-survey prep

## Picklist
PROGRESS
Not Started
In Progress
Complete
Barriers